## Defects
Defect # | Status | Raised By | Tested on Version | TestCase Id | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity
1 | Open | Expert | v1 | NC4 | 1)Enter Blank space as the first character in Customer Name Field | An error message "First character can not be space" must show | An error message "Numbers are not allowed" is shown | Medium | Medium
2 | Open | Expert | v1 | NC5 | 1) Do not enter a value in Address Field 2) Press Tab and move to the next field | An error message "Address must not be blank" must show | System does not show error message | Medium | Medium
3 | Open | Expert | v1 | NC6 | 1) Enter Blank space as the first character in Address field | An error message "First character can not be space" must show | System does not show error message | Medium | Medium
4 | Open | Expert | v1 | NC7 | 1) Enter Special characters in Address Field | An error message "Special characters are not allowed" must show | System does not show error message
5 | Open | Expert | v1 | NC11 | 1)Enter Blank space as the first character in City Field | An error message "First character can not be space" must show | An error message "Numbers are not allowed" is shown | Medium | Medium
6 | Open | Expert | v1 | NC15 | 1)Enter Blank space as the first character in State Field | An error message First character can not be space" must show | An error message "Numbers are not allowed" is shown | Medium | Medium
7 |  | Expert
8 | Open | Expert | v1 | NC20 | 1)Enter Blank space as the first character in Pin Code Field | An error message "First character can not be space" must show | System does not show error message | Medium | Medium
9 | Open | Expert | v1 | NC26 | 1)Enter Blank space as the first character in Telephone Number Field | An error message "First character can not be space" must show | System does not show error message | Medium | Medium
10 |  | Expert
11 | Open | Expert | v1 | NC29 | 1)Enter Blank space as the first character in Email Field | An error message "First character can not be space" must show | System does not show error message | Medium | Medium
12 | Open | Expert | v1 | EC2 | 1) Enter character value in Customer ID Field | An error message "Character are not allowed" must shown | 1)In the first test data, An error message "Characters are not allowed" is shown 2)In the second test data, System does not show | High | High
13 | Open | Expert | v1 | EC4 | 1) Enter Valid Customer ID 2)Submit | Edit Customer successfully redirect to Edit Customer Page | System display "Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | High
14 | Open | Expert | v1 | EC5 | 1) Do not enter a value in Customer Name Field 2) Press Tab and move to next Field | An error message "Customer name must not be blank" must shown | Cannot be executed due to connection issue | High | High
15 | Open | Expert | v1 | EC6 | 1) Enter numeric value in Customer Name Field | An error message "Number are not allow" must shown | Cannot be executed due to connection issue | High | High
16 | Open | Expert | v1 | EC7 | 1) Enter Special characters in Customer Name Field | An error message "Special characters are not allowed" must show | Cannot be executed due to connection issue | High | High
17 | Open | Expert | v1 | EC8 | 1)Enter Blank space as the first character in Customer Name Field | An error message "First character can not be space" must show | Cannot be executed due to connection issue | High | High
18 | Open | Expert | v1 | EC9 | 1) Do not enter a value in Address Field 2) Press Tab and move to the next field | An error message "Address must not be blank" must show | Cannot be executed due to connection issue | High | High
19 | Open | Expert | v1 | EC10 | 1) Enter Blank space as the first character in Address field | An error message "First character can not be space" must show | Cannot be executed due to connection issue | High | High
20 | Open | Expert | v1 | EC11 | 1) Enter Special characters in Address Field | An error message "Special characters are not allowed" must show | Cannot be executed due to connection issue | High | High
21 | Open | Expert | v1 | EC12 | 1) Do not enter a value in City Field 2) Press Tab and move to next Field | An error message "City Field must not be blank" must shown | Cannot be executed due to connection issue | High | High
22 | Open | Expert | v1 | EC13 | 1) Enter numeric value in City Field | An error message "Numbers are not allowed" must shown | Cannot be executed due to connection issue | High | High
23 | Open | Expert | v1 | EC14 | 1) Enter Special characters in City Field | An error message "Special characters are not allowed" must show | Cannot be executed due to connection issue | High | High
24 | Open | Expert | v1 | EC15 | 1)Enter Blank space as the first character in City Field | An error message "First character can not be space" must show | Cannot be executed due to connection issue | High | High
25 | Open | Expert | v1 | EC16 | 1) Do not enter a value in State Field 2) Press Tab and move to next Field | An error message "State must not be blank" must shown | Cannot be executed due to connection issue | High | High
26 | Open | Expert | v1 | EC17 | 1) Enter numeric value in State Field | An error message "Numbers are not allowed" must shown | Cannot be executed due to connection issue | High | High
27 | Open | Expert | v1 | EC18 | 1) Enter Special characters in State Field | An error message "Special characters are not alloweds" must show | Cannot be executed due to connection issue | High | High
28 | Open | Expert | v1 | EC19 | 1)Enter Blank space as the first character in State Field | An error message "First character can not be space" must show | Cannot be executed due to connection issue | High | High
29 | Open | Expert | v1 | EC20 | 1) Do not enter a value in Pin Code Field 2) Press Tab and move to next Field | An error message "Pin code must not be blank" must shown | Cannot be executed due to connection issue | High | High
30 | Open | Expert | v1 | EC21 | 1) Enter character value in Pin Code Field | An error message "Characters are not allowed" must shown | Cannot be executed due to connection issue | High | High
31 | Open | Expert | v1 | EC22 | 1) Enter Special characters in Pin Code Field | An error message "Special characters are not allowed" must show | Cannot be executed due to connection issue | High | High
32 | Open | Expert | v1 | EC23 | 1)Enter a value that has blank space | An error message "Characters are not allowed" must show | Cannot be executed due to connection issue | High | High
33 | Open | Expert | v1 | EC24 | 1)Enter Blank space as the first character in Pin Code Field | An error message "First character can not be space" must show | Cannot be executed due to connection issue | Medium | Medium
34 | Open | Expert | v1 | EC25 | 1)Enter a value more than 6 digits 2)Enter a value less than 6 digits | An error message "Pin code must have 6 digits" must show | Cannot be executed due to connection issue | Medium | Medium
35 | Open | Expert | v1 | EC26 | 1) Do not enter a value in Telephone Number Field 2) Press Tab and move to next Field | An error message "Telephone Number must not be blank" must shown | Cannot be executed due to connection issue | Medium | Medium
36 | Open | Expert | v1 | EC27 | 1) Enter character value in Telephone Number Field | An error message "Characters are not allowed" must shown | Cannot be executed due to connection issue | Medium | Medium
37 | Open | Expert | v1 | EC28 | 1) Enter Special characters in Telephone Number Field | An error message "Special characters are not allowed" must show | Cannot be executed due to connection issue | Medium | Medium
38 | Open | Expert | v1 | EC29 | 1)Enter a value that has blank space | An error message "Characters are not allowed" must show | Cannot be executed due to connection issue | Medium | Medium
39 | Open | Expert | v1 | EC30 | 1)Enter Blank space as the first character in Telephone Number Field | An error message "First character can not be space" must show | Cannot be executed due to connection issue | Medium | Medium
40 | Open | Expert | v1 | EC31 | 1) Do not enter a value in Email Field 2) Press Tab and move to next Field | An error message "Email must not be blank" must shown | Cannot be executed due to connection issue | Medium | Medium
41 | Open | Expert | v1 | EC32 | 1) Enter a valid email | An error message "Email must not be valid" must shown | Cannot be executed due to connection issue | Medium | Medium
42 | Open | Expert | v1 | EC33 | 1)Enter Blank space as the first character in Email Field | An error message "First character can not be space" must show | Cannot be executed due to connection issue | Medium | Medium
43 | Open | Expert | v1 | DC2 | 1) Enter character value in Customer ID Field | An error message "Characters are not allowed" must shown | 1)In the first test data, An error message "Characters are not allowed" is shown 2)In the second test data, System does not show | Medium | Medium
44 | Open | Expert | v1 | DC5 | 1)Enter Blank space as the first character in Customer ID Field | An error message "First character can not be space" must show | System does not show error message | Medium | Medium
45 | Open | Expert | v1 | NA1 | 1) Do not enter a value in Customer ID Field 2) Press Tab and move to next Field | An error message "Customer ID must not be blank" must shown | System does not show error message | Medium | Medium
46 | Open | Expert | v1 | NA2 | 1) Enter character value in Customer ID Field | An error message "Characters are not allowed" must shown | System does not show error message | Medium | Medium
47 | Open | Expert | v1 | NA3 | 1) Enter Special characters in Customer ID Field | An error message "Special characters are not allowed" must show | System does not show error message | Medium | Medium
48 | Open | Expert | v1 | NA4 | 1)Enter a value that has blank space | An error message "Characters are not allowed" must shown | System does not show error message | Medium | Medium
49 | Open | Expert | v1 | NA5 | 1)Enter Blank space as the first character in Customer ID Field | An error message "First character can not be space" must show | System does not show error message | Medium | Medium
50 | Open | Expert | v1 | NA6 | 1) Do not enter a value in Initial Deposit Field 2) Press Tab and move to next Field | An error message "Initial Deposit must not be blank" must shown | System does not show error message | Medium | Medium
51 | Open | Expert | v1 | NA7 | 1) Enter character value in Initial Deposit Field | An error message "Characters are not allowed" must shown | System does not show error message | Medium | Medium
52 | Open | Expert | v1 | NA8 | 1) Enter Special characters in Initial Deposit Field | An error message "Special characters are not allowed" must show | System does not show error message | Medium | Medium
53 | Open | Expert | v1 | NA9 | 1)Enter a value that has blank space | An error message "Characters are not allowed" must shown | System does not show error message | Medium | Medium
54 | Open | Expert | v1 | NA10 | 1)Enter Blank space as the first character in Initial Deposit Field | An error message "First character can not be space" must show | System does not show error message | Medium | Medium
55 | Open | Expert | v1 | EA4 | 1)Enter a value that has blank space | An error message "Account No must not have space" must show | An error message "Characters are not allowed" is shown | High | High
56 | Open | Expert | v1 | EA5 | 1)Enter Blank space as the first character in Account No Field | An error message "First character can not be space" must show | System does not show error message | High | High
57 | Open | Expert | v1 | EA6 | 1) Enter valid account number 2) Submit | Edit Account succesfully Redirect to Edit Account Form | System shows "Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | High
58 | Open | Expert | v1 | EA7 | 1) Do not enter a value in Customer ID Field 2) Press Tab and move to next Field | An error message "Customer ID must not be blank" must shown | Cannot execute due to connection issue | High | High
59 | Open | Expert | v1 | EA8 | 1) Enter character value in Customer ID Field | An error message "Characters are not allowed" must shown | Cannot execute due to connection issue | High | High
60 | Open | Expert | v1 | EA9 | 1) Enter Special characters in Customer ID Field | An error message "Special characters are not allowed" must show | Cannot execute due to connection issue | High | High
61 | Open | Expert | v1 | EA10 | 1)Enter a value that has blank space | An error message "Characters are not allowed" must shown | Cannot execute due to connection issue | High | High
62 | Open | Expert | v1 | EA11 | 1)Enter Blank space as the first character in Customer ID Field | An error message "First character can not be space" must show | Cannot execute due to connection issue | High | High
63 | Open | Expert | v1 | EA12 | 1) Do not enter a value in Balance Field 2) Press Tab and move to next Field | An error message "Balance must not be blank" must shown | Cannot execute due to connection issue | High | High
64 | Open | Expert | v1 | EA13 | 1) Enter character value in Balance Field | An error message "Characters are not allowed" must shown | Cannot execute due to connection issue | High | High
65 | Open | Expert | v1 | EA14 | 1) Enter Special characters in Balance Field | An error message "Special characters are not allowed" must show | Cannot execute due to connection issue | High | High
66 | Open | Expert | v1 | EA15 | 1)Enter a value that has blank space | An error message "Characters are not allowed" must show | Cannot execute due to connection issue | High | High
67 | Open | Expert | v1 | EA16 | 1)Enter Blank space as the first character in Balance Field | An error message "First character can not be space" must show | Cannot execute due to connection issue | High | High
68 | Open | Expert | v1 | DA5 | 1)Enter Blank space as the first character in Account No Field | An error message "First character can not be space" must show | System does not show error message | High | High
69 | Open | Expert | v1 | MS5 | 1)Enter Blank space as the first character in Account Number Field | An error message "First character can not be space" must show | System does not show error message | Medium | Medium
70 | Open | Expert | v1 | CS4 | 1)Enter a value that has blank space | An error message "Characters are not allowed" must shown | An error message "Characters are not allowed" is shown | Medium | Medium
71 | Open | Expert | v1 | CS5 | 1)Enter Blank space as the first character in Account Number Field | An error message "First character can not be space" must show | System does not show error message | Medium | Medium
72 | Open | Expert | v1 | CS6 | 1) Do not enter a value in Amount Lower Limit Field 2) Press Tab and move to next Field | An error message "Amount Lower Limit is required" must shown | System does not show error message | Medium | Medium
73 | Open | Expert | v1 | CS7 | 1) Enter character value in Amount Lower Limit Field | An error message "Characters are not allowed" must shown | System does not show error message | Medium | Medium
74 | Open | Expert | v1 | CS8 | 1) Enter Special characters in Amount Lower Limit Field | An error message "Special characters are not allowed" must show | System does not show error message | Medium | Medium
75 | Open | Expert | v1 | CS9 | 1)Enter a value that has blank space | An error message "Characters are not allowed" must shown | System does not show error message | Medium | Medium
76 | Open | Expert | v1 | CS10 | 1)Enter Blank space as the first character in Amount Lower Limit Field | An error message "First character can not be space" must show | System does not show error message | Medium | Medium
77 | Open | Expert | v1 | CS11 | 1) Do not enter a value in Number of Transaction Field 2) Press Tab and move to next Field | An error message "Number of Transaction must not be blank" must shown | System does not show error message | Medium | Medium
78 | Open | Expert | v1 | CS12 | 1) Enter character value in Number of Transaction | An error message "Characters are not allowed" must shown | System does not show error message | Medium | Medium
79 | Open | Expert | v1 | CS13 | 1) Enter Special characters in Number of Transaction Field | An error message "Special characters are not allowed" must show | System does not show error message | Medium | Medium
80 | Open | Expert | v1 | CS14 | 1)Enter a value that has blank space | An error message "Number of Transaction must not have space" must show | System does not show error message | Medium | Medium
81 | Open | Expert | v1 | CS15 | 1)Enter Blank space as the first character in Number of Transaction Field | An error message "First character can not be space" must show | System does not show error message | High | High
82 | Open | Expert | v1 | IP1 | 1) Enter all required fields 2) Submit | Message Should be display "Customer added successfully !!" | Screen displays "Connection failed: Access denied for user 'root'@'localhost' (using password: NO)" | High | High
83 | Open | Expert | v1 | IP2 | 1) Enter all required field with existing user data 2) Submit | Message Should be displayed"Email address already exist" | Connection error | High | High
84 | Open | Expert | v1 | IP3 | 1) Enter all required fields 2) Submit | Message Should be displayed" customer records updated successfully!!" | Connection error | High | High
85 | Open | Expert | v1 | IP4 | 1) Enter all required fields 2) Submit | Message Should be display" customer records updated successfully!!" | Connection error | High | High
86 | Open | Expert | v1 | IP5 | 1) Enter the required fields 2) Submit | Message Should be display" You are not authorise to edit this customer!!" | Connection error | High | High
87 | Open | Expert | v1 | IP6 | 1) Enter all required fields 2) Submit | Message Should be display " account generated successfully" | Connection error | High | High
88 | Open | Expert | v1 | IP7 | 1) Enter all fields with customer id and account type already exist | Message Should be display " account generated successfully" | Connection error | High | High
89 | Open | Expert | v1 | IP8 | 1) Enter Account Number 2) Submit | Display Generated ministatement | Connection error | High | High
90 | Open | Expert | v1 | IP9 | 1) Enter account number 2) Submit | Message Should be display " account detail successfully updated" | Connection error | High | High
91 | Open | Expert | v1 | IP10 | 1) Enter all required fields 2) Submit | Display Generated ministatement | Connection error | High | High
92 | Open | Expert | v1 | IP11 | 1) Enter all required fields 2) Submit | Message Should be display"Account deleted Successfully" | Connection error | High | High
93 | Open | Expert | v1 | IP12 | 1) Enter all required fields 2) Submit | Message Should be display"Account does not exist " | Connection error | High | High
94 | Open | Expert | v1 | IP13 | 1) Enter all required fields 2) Submit | Message Should be display"Account does not exist " | Connection error | High | High
95 | Open | Expert | v1 | IP14 | 1)Enter all required field of deleted account 2)Submit | Message Should be display - "Account does not exist" | Connection error | High | High
96 | Open | Expert | v1 | IP15 | 1) Enter all required fields 2) Submit | Message Should be display"Customer could not be deleted " | Connection error | High | High
97 | Open | Expert | v1 | IP16 | 1)Enter all required field of deleted account 2)Submit | Message Should be display "You are not authorise to delete this account " | Connection error | High | High
98 | Open | Expert | v1 | IP17 | 1) Enter Account Number 2) Submit | Displayed Generated ministatement | Connection error | High | High
99 | Open | Expert | v1 | IP18 | 1) Enter all required fields 2) Submit | Display Generated Customized statement | Connection error | High | High
100 | Open | Expert | v1 | Exploratory Testing | Check the Name of the Website | Guru99 Bank | Gtpl Bank | High | Low